## Project milestones
Project 1 | GOAL IS 100/100
Team Members:
Eder Ortiz | Data creation and gathering ¦ Coding | Technology Field | Data Networks
Demilade Adenuga | Data Analysis and presentation¦ Storytelling | Accounting Field | Consultant
Geraldine Valencia | Data gathering and analysis | Banking Industry | Advisor¦ Engineering background
Relevant Modules: | Module 4 - Module 6 ¦ Tuesday (28/01/25) & Thursday class (30/01/25)
Suggestions on Timing:
Revise | Feb 11th [9:30 - 11:00PM Toronto time] Tuesday
Submission | Feb 12th [6:30 - 9:30PM Toronto time] Wednesday
Days and Plan for each day till Feb 13th
[6 empty] | Monday | 2025-02-03 | 6:30-9:30 | Summarize - 20mins to Geraldine
Project Milestones |  | Planned Date | Start Date | Status | Completion Date
Project Planning |  | 2025-02-01 | 2025-02-01 | Complete | 2025-02-03 | Tuesday | 2025-02-04 | 6:30-9:30PM | Group call
Select Dataset | Choose the data you are interested in or the data easier to work with to achieve this assignment. | 2025-02-01 | 2025-02-01 | Complete | 2025-02-03 |  |  |  | Create a repository
Review Dataset |  | 2025-02-03 | 2025-02-04 | Complete | 2025-02-06 |  |  |  | Add the Collaborators
Create Repository | One team member to create¦include git ignore & READ ME | 2025-02-03 | 2025-02-04 | Complete | 2025-02-04 |  |  |  | We need everyone Github username
What is the Hypothesis? | What is the overarching theme - 2 major points | 2025-02-03 | 2025-02-04 | Complete | 2025-02-05 |  |  |  | Review
Analysis/ Data visualizations | Pandas/ Matplotlib/Numpy/scipy / API | 2025-02-05 | 2025-02-04 | Complete | 2025-02-10
Testing/Results |  | 2025-02-07 | 2025-02-07 | Complete | 2025-02-10 | Tuesday/ Wednesday | 2025-02-05 |  | Eder to do some of the cleaning | Duplicate or missing values
Documentation of analysis and results | This will be added to presentation deck | 2025-02-09 | 2025-02-11 | Complete | 2025-02-11 | Thursday | 2025-02-06 |  | Team to work on Hypothesis | Team to do git pull
Combination of Jupyter notebook | Combining all analysis into one jupyter notebook | 2025-02-10 | 2025-02-10 | Complete | 2025-02-11 | Weekend - Sunday | 2025-02-09 |  | Team to finish on Hypothesis
Presentation Deck - 5/6 pager | 2 major points will determine the flow of the deck and the storyline | 2025-02-10 |  | Not Started
Share presentation across all the members | All team members will present, turn on our cameras | 2025-02-10 | 2025-02-11 | Complete | 2025-02-11 | Next week
READ ME File | A nice READ ME file that tells the overview | 2025-02-11 | 2025-02-11 | Complete | 2025-02-11 | Monday | 2025-02-10 | 6:30-9:30PM/11PM | Combination into 1 jupyter notebook
Submission |  | 2025-02-12 | 2025-02-12 | Complete | 2025-02-12 | Tuesday | 2025-02-11 | 6:30-9:30PM/11PM | READ ME FILE & Analysis
[6 empty] | Wednesday | 2025-02-12 | 6:30-9:30PM/11PM | READ ME FILE & Analysis + Presentation of storyline
Submit asignment
Project Guidelines | [8 empty] | Teammates Feedback - strengths
Have different jupyter Notebooks | Ensure we have separate notebooks for each activity with data anlaysis
Then copy all jupyter notebooks into one

## Data Ideation_Fetching
| RAG status | Working SMARTLY
1 | Options | Overarching Themes | Issues
2 | Netflix | Who is the common actor? Rating? Which shows are common to countries? | Less numerical data which may require more work and understanding
3 | Finance | Could not figure questions | Too complex
4 | Samsung Phone Data | Various correlations between the numbers and we had a cheat sheet that was perfect | Data too short
5 | Uber Trips | Is weekend more busy than weekdays? Correlation between active vehicles and trips? | To convert date to know weekend and weekdays
6 | Health App | Various correlations between the numbers | No cheat sheet
7 | World Happiness | In 2015 - people were more happy and more focused on money | Not up to 5,000 rows | https://www.kaggle.com/datasets/unsdsn/world-happiness
Time analysis, regression, correlation heat map, focus trend analysis
showing the year in a column - add new column 'Year' after merging
preference has changed over time. What Makes A country Happy? What Makes You happy?
Couple of cheat sheets - not exact but we can combine based on visualization
8 | Internshala dataset | Had over 5000 rows | More skewed to India as a location and mixed data (numbers and text)
9 | Exploring 5000 Inc |  |  | https://www.kaggle.com/code/thabresh/exploring-inc-5000-companies/notebook
11 | Car price | mileage and condition¦ drop vin, drop , the car and the selling proce
|  | Question to Mizanur - How to get the Kaggle API Key | Using Fitness App one if Mizanur can explain how to use the API to pull the information
May need to install a kaggle module in Python
FINAL OPTION
| Telco Customer Churn | Which generation churned out more, correlation age and churn,gender on churn, multiple service |  | https://www.kaggle.com/code/bhartiprasad17/customer-churn-prediction